## Issue-Log
ISSUE MANAGEMENT LOG
Project Name: |  |  | Eventual 1/2023
Project Manager Name: |  |  | Alessia Rocco, Francesco Foschini
ID | Status | Priority | Issue Description | Owner | Estimated Resolution Date | Escalation Needed (Y/N)? | Impact | Actions | Date Identified | Logged By | Actual Resolution/Completion Date | Final Resolution & Follow-on actions
001 | Open | Critical | Aggiornamento degli eventi lancia errore di scrittura nel database. |  |  | Yes | Potential project cancellation or significant delay. | Meet with board members to review the business case and revise the investment appraisal if needed. |  | dev4 |  | The project sponsor reviewed the investment appraisal and presented the busienssd case with revisions.
002 | Work In Progress | High | Cambiamento id autore genera un conflitto nell'update del database. |  |  | No | Delay to start of project design phase. | Fix sessions |  | dev1 |  | Recruited on fixed term contract 01/08. Review in 2 months, see task ID 202 on the project schedule.
003 | Closed | Medium | Contatore dei partecipanti errato. |  |  | Yes | May be forced to level the plan to fit resource availability which will delay target go live date. | Meet with department heads to review resource plans and re-prioritise work. |  | dev2
004 | Work In Progress | Low | Logout al caricamento della pagina nel browser |  |  | No |  |  |  | dev3

## severity-levels
Issue severity | Description
Critical | Issue will stop project progress.
High | Issue will likely impact budget, schedule or scope.
Medium | Issue impact the project, but could be mitigated to avoid an impact on budget, schedule or scope.
Low | Issue is low impact and/or low effort to resolve.
| This template was provided by | https://www.stakeholdermap.com/